## M1
<9900-M18D-DONUT> MEETING MINUTES
Meeting #1
Date | 2026-02-27
Time | 5:00pm - 6:00 pm (60 minutes)
Time Keeper | Teams
Attendees | Aakarsh, Aditya, Kushagra, Rachael, Saloni, Santhosh
Apologies | -
Please bring/read | Project specifications
Other resources | -
Meeting purpose | Discussion before Client Meeting
Next Meeting | 2026-03-01
Agenda
Item | Agenda Item | Assignee | Notes
1 | Discussion on the understanding of the project specifications by all team members | All
2 | Discussion on questions/doubts to ask Client on the project | All
3 | Further Research to be conducted before the next meeting | All
Open Actions
Item | Action/Discussed | Deadline
1 | Mock initial design for Project proposal | 2026-03-01
2 | Research on backend handing & DB | 2026-03-01
3 | Researching API querying, AI solutions/models accuracy cost resources require, addtionally, cloud computing vs local storage | 2026-03-01
4 | Researching terminology translation architecture | 2026-03-01
Questions for Mentor
None
Questions for Client
https://docs.google.com/document/d/1AO9sqgGi36wE5YcLkNQ6_qUigaywdb31z0wke3ll6ss/edit?tab=t.0

## M1 (Client)
<9900-M18D-DONUT> MEETING MINUTES
Meeting #1 (With Client)
Date | 2026-03-01
Time | 3:30pm -4:00 pm (30 minutes)
Time Keeper | Teams
Attendees | Aakarsh, Aditya, Kushagra, Rachael, Saloni, Santhosh, Md Abu Rayhan
Apologies | -
Please bring/read | Project specifications
Other resources | -
Meeting purpose | Initial Client Consultation — TRIBOT Multilingual Clinical Translation Project Clarify scope, requirements, constraints, and expectations
Next Meeting | 2026-03-16
Agenda
Item | Agenda Item | Assignee | Notes
1 | Project overview and objectives: | All | TRIBOT assists triage nurses in emergency departments Uses Australia Triage Scale (ATS 1–5) Focus: multilingual communication with patients Main language focus: Arabic Existing prototype already tested
2 | Scope of translation work | All | 1. Translation is primary task for this team 2. Multilingual allowed but Arabic prioritized 3. Translation occurs after speech-to-text transcription 4. Real-time translation preferred, batch acceptable
3 | Data availability and constraints | All | 1. Real healthcare datasets cannot be shared (privacy/legal) 2. Students should create synthetic datasets 3. Possible public sources may be provided later 4. Client may share example data only
4 | Model accuracy expectations | All | 1. Target performance ~85–89% accuracy or better 2. Accuracy can be evaluated using triage role-play scenarios
5 | Medical terminology handling | All | 1. Need accurate translation of clinical terms 2. Keyword extraction or summary desirable 3. Important terms should be highlighted
6 | Technical stack recommendations | All | 1. Frontend: React + TypeScript preferred 2. Backend: FastAPI recommended 3. Cloud: Azure or AWS suggested 4. Use reputable models with guardrails
7 | 7. Design guidance | All | User-centered design for triage nurses 1.Low cognitive load 2. Simple workflow interface 3. No fixed UI template required
8 | Compliance and ethics considerations | All | 1. Must follow healthcare policies and safety guidelines 2. Avoid unsafe or unregulated AI tools 3.Guardrails important due to patient safety impact
9 | Integration considerations | All | 1. System likely part of multi-team project 2. Integration with transcription team uncertain 3. Collaboration rules to be confirmed
10 | Project logistics | All | 1. No confirmed cloud credits from university 2. Azure student credits (~$200) available individually 3. Open-source solutions allowed
Open Actions
Item | Action/Discussed | Deadline
1 | Create synthetic dataset for translation training/testing | Ongoing
2 | Research translation models suitable for medical context | Ongoing
3 | Investigate public medical terminology sources | Ongoing
4 | Design system architecture (frontend + backend) | Ongoing
5 | Ensure compliance and guardrail considerations | Ongoing
Questions for Mentor
None
Questions for Client
https://docs.google.com/document/d/1AO9sqgGi36wE5YcLkNQ6_qUigaywdb31z0wke3ll6ss/edit?tab=t.0

## M2
<9900-M18D-DONUT> MEETING MINUTES
Meeting #2
Date | 2026-03-06
Time | 9:00pm -9.30 pm (30 minutes)
Time Keeper | Teams
Attendees | Aakarsh, Aditya, Kushagra, Rachael, Saloni, Santhosh, Md Abu Rayhan
Apologies | -
Please bring/read | Project specifications
Other resources | Proposal template and assignment requirements
Meeting purpose | Discuss project proposal preparation for submission due 07/03/2026 at 9:00 pm, assign responsibilities, and confirm deliverables
Next Meeting | TBD
Agenda
Item | Agenda Item | Assignee | Notes
1 | Review of project proposal requirements | All | Deadline confirmed: 07/03/2026, 9:00 pm Specification link shared by team Required sections discussed
2 | Division of tasks for proposal | All | Backend development section: Saloni System architecture diagram: Aditya User stories & sprint planning (Jira): Rachael & Kushagra Scope statement: Rachael (already completed prior to meeting) Project background: Rachael & Aakarsh Mock user storyboard / interface concept: Rachael & Saloni Timeline & overall document drafting: Santhosh Review, audit, corrections, redesign: Santhosh Team acknowledged requirement to send scope statement to client Kushagra confirmed it had already been prepared Remaining proposal components assigned to Aakarsh and Santhosh Team agreed to collaborate to meet deadline
Open Actions
Item | Action/Discussed | Deadline
1 | Complete assigned proposal sections | 2026-03-07
2 | Compile final proposal document | 2026-03-07
3 | Review and proofread submission | 2026-03-07
4 | Submit proposal before deadline | 2026-03-07 21:00
Questions for Mentor
None
Questions for Client
https://docs.google.com/document/d/1AO9sqgGi36wE5YcLkNQ6_qUigaywdb31z0wke3ll6ss/edit?tab=t.0

## M3
<9900-M18D-DONUT> MEETING MINUTES
Meeting #3
Date | 2026-03-06
Time | 9:00pm -9.30 pm (30 minutes)
Time Keeper | Teams
Attendees | Aakarsh, Aditya, Kushagra, Rachael, Saloni, Santhosh, Md Abu Rayhan
Apologies | -
Please bring/read | Project specifications
Other resources | Proposal template and assignment requirements
Meeting purpose | Discuss project proposal preparation for submission due 07/03/2026 at 9:00 pm, assign responsibilities, and confirm deliverables
Next Meeting | TBD
Agenda
Item | Agenda Item | Assignee | Notes
1 | Review of project proposal requirements | All | Deadline confirmed: 07/03/2026, 9:00 pm Specification link shared by team Required sections discussed
2 | Division of tasks for proposal | All | Backend development section: Saloni System architecture diagram: Aditya User stories & sprint planning (Jira): Rachael & Kushagra Scope statement: Rachael (already completed prior to meeting) Project background: Rachael & Aakarsh Mock user storyboard / interface concept: Rachael & Saloni Timeline & overall document drafting: Santhosh Review, audit, corrections, redesign: Santhosh Team acknowledged requirement to send scope statement to client Kushagra confirmed it had already been prepared Remaining proposal components assigned to Aakarsh and Santhosh Team agreed to collaborate to meet deadline
Open Actions
Item | Action/Discussed | Deadline
1 | Complete assigned proposal sections | 2026-03-07
2 | Compile final proposal document | 2026-03-07
3 | Review and proofread submission | 2026-03-07
4 | Submit proposal before deadline | 2026-03-07 21:00
Questions for Mentor
None
Questions for Client
https://docs.google.com/document/d/1AO9sqgGi36wE5YcLkNQ6_qUigaywdb31z0wke3ll6ss/edit?tab=t.0

## M4
<9900-M18D-DONUT> MEETING MINUTES
Meeting #4
Date | 2026-03-10
Time | 1:00pm -1.30 pm (30 minutes)
Time Keeper | Teams
Attendees | Aakarsh, Aditya, Kushagra, Rachael, Saloni, Santhosh
Apologies | -
Please bring/read | Sprint backlog and user stories (Jira) Synthetic dataset provided by client
Other resources | Sprint 1 tasks Product demo requirements
Meeting purpose | Plan Sprint 1 tasks, clarify scope of work, prepare for upcoming product demo, and assign responsibilities
Next Meeting | 2026-03-15
Agenda
Item | Agenda Item | Assignee | Notes
1 | Discussion of client-provided synthetic dataset | All | Dataset consists of ~50 triage scenarios in English Primarily related to ATS (Australian Triage Scale) classification Team concluded dataset is not directly suitable for translation model training Need verified English–Arabic translation dataset instead Possible use of open-source datasets identified
2 | Sprint 1 scope clarification | All | Sprint 1 will focus on building a minimal working prototype for demo: Basic translation functionality Frontend interface Backend API Initial AI model development Integration readiness
3 | Selection of features for product demo | All | Translation capability is the primary feature to demonstrate Login functionality optional (not required for demo but may be included) Additional advanced features (e.g., red-flag detection, confidence scoring) deferred to later sprints
4 | Task allocation for Sprint 1 | All | Frontend Development Santhosh Kumar Radhakrishnan Aakarsh Hajela Tasks: Basic UI implementation Homepage and translation interface Optional login page for completeness Backend Development & Database Saloni Mahendra Jain Rachael Thomas Tasks: API endpoints Database setup Authentication (if required) Integration with translation model AI Model & Data Processing Aditya Aditya Kushagra Khatri Tasks: Translation model development Dataset identification and preparation Data preprocessing pipeline Model training
5 | Development approach |  | Work can proceed in parallel across teams Frontend initially independent Backend to expose APIs for integration Model accessible via API calls Final integration to occur before demo
6 | GitHub workflow agreement | All | Team agreed to: Use feature-based branching Collaborate on shared branches per feature Merge via pull requests once complete
7 | Timeline planning | All | Individual tasks to be completed by Saturday/Sunday Internal integration meeting scheduled Sunday morning Buffer time reserved for troubleshooting Presentation preparation to follow
8 | Product demo preparation | All | Demo requirements discussed: Working prototype demonstration Presentation slides required Possible recording of demo (to be confirmed) Each member may present their component
9 | Client communication | All | Client prefers meetings at previously agreed time Next client meeting tentatively Monday
Open Actions
Item | Action/Discussed | Deadline
1 | Identify suitable English–Arabic dataset | ASAP
2 | Develop basic translation model | Before demo
3 | Implement frontend interface | Before demo
4 | Implement backend APIs and database | Before demo
5 | Integrate components into working prototype | Before demo
6 | Prepare presentation slides | Before demo
7 | Confirm demo recording requirements | Before demo
Questions for Mentor
Clarification on demo requirements and recording expectations
Questions for Client
https://docs.google.com/document/d/1AO9sqgGi36wE5YcLkNQ6_qUigaywdb31z0wke3ll6ss/edit?tab=t.0

## M5
<9900-M18D-DONUT> MEETING MINUTES
Meeting #5
Date | 2026-03-15
Time | 9:00am -10:00am (1 hour)
Time Keeper | Teams
Attendees | Aakarsh, Aditya, Kushagra, Rachael, Saloni, Santhosh
Apologies | -
Please bring/read | Current codebase, UI prototypes, dataset resources
Other resources | GitHub repository Figma design files Sprint backlog
Meeting purpose | Review Sprint 1 progress, resolve technical issues, prepare working prototype for tutor demo, and coordinate integration of components
Next Meeting | 15/03/2026 8pm
Agenda
Item | Agenda Item | Assignee | Notes
1 | GitHub collaboration issues | All | Team encountered difficulties cloning and pushing to the private repository Issues related to SSH keys, permissions, and accounts Agreed to push code to branches and merge later Repository access and workflow clarified
2 | Frontend prototype review | All | Frontend implemented based on Figma design Contains placeholder features for demo UI adjustments required to match updated proposal design Decision to simplify interface for demo purposes Changes agreed: Remove patient details section Keep translation interface as primary feature Retain history tab (audit log) Retain terminology/glossary tab
3 | Functional scope clarification | All | Based on client requirements: Application primarily for doctor/triage nurse use No need to capture detailed patient information initially Focus on immediate translation capability Patient data handling may be added later
4 | Translation model progress | All | Translation functionality identified as the core demo requirement Initial version will perform general translation only Medical terminology handling deferred due to lack of dataset Multilingual model selected capable of supporting many languages Dataset discussion: Difficulty obtaining medical Arabic datasets Possible use of public sources or scraped content Backup options considered
5 | Terminology / glossary feature | All | Glossary planned as searchable database of medical terms Terminology tab will display language pairs Database integration to be implemented later Placeholder content acceptable for demo
6 | Audit logs and session tracking | All | Backend stores translation logs using session IDs Logs retrievable via API endpoint Logs will be displayed in the history tab Audit logs for system errors remain backend-only
7 | Integration planning | All | Backend and model components to be integrated with frontend Backend code to be pushed to repository for access Frontend integration to follow
8 | Patient data handling discussion | All | Team explored options for storing interaction records: Translation should start immediately without requiring data Patient identification may be added after interaction Possible approaches discussed: Assign internal IDs automatically Allow nurse to enter identifying details later Use history tab to retrieve conversations Decision: Prioritize speed of use in emergency context Patient data features deferred to later versions
9 | Demo preparation strategy | All | Minimum demo requirements identified: Working translation functionality Functional UI Backend connectivity Placeholder features acceptable Additional demo elements: Terminology tab (optional) History/audit log view Dummy content allowed for non-core features
| Immediate task allocation | All | Aditya: Implement working translation model within a few hours Santhosh: Modify frontend and remove unnecessary sections Saloni: Push backend code and prepare APIs Rachael: Collect datasets and prepare presentation slides Team to reconvene later for progress review
| Presentation preparation | All | Presentation slides required for demo Rachael assigned to prepare PPT Team aims to complete most work before next meeting
Open Actions
Item | Action/Discussed | Deadline
1 | Resolve GitHub access issues | Immediate
2 | Implement working translation feature | Before demo
3 | Update frontend to match proposal scope | Before demo
4 | Integrate backend with frontend | Before demo
5 | Prepare presentation slides | Before demo
6 | Collect usable datasets | Ongoing
7 | Conduct internal review meeting | Same day (8:00 pm)
Questions for Mentor
None
Questions for Client
None

## M6
<9900-M18D-DONUT> MEETING MINUTES
Meeting #6
Date | 2026-03-15
Time | 8:00pm -9:00 pm (1 hour)
Time Keeper | Teams
Attendees | Aakarsh, Aditya, Kushagra, Rachael, Saloni, Santhosh
Apologies | -
Please bring/read | Sprint 1 deliverables Draft presentation content Demo progress updates
Other resources | Architecture diagram Frontend prototype Backend implementation
Meeting purpose | Coordinate preparation for product demo and tutorial presentation, assign speaking roles, review technical progress, and plan integration completion
Next Meeting | 16/03/2026 9am
Agenda
Item | Agenda Item | Assignee | Notes
1 | Presentation slide preparation | All | Slides will follow required content structure Rachael volunteered to prepare the main presentation deck Team members will provide content for their respective sections Script notes may be generated to support speakers Planned slide topics: Background and problem statement System architecture Backend overview Future development plans
2 | Division of presentation responsibilities | All | AI Model Explanation Aditya to present model details Key points to include: Use of Small-100 multilingual encoder-decoder model Lightweight architecture suitable for real-time translation Supports over 100 languages and many translation directions Current implementation limited to English ↔ Arabic Future plan: integrate NER-based medical terminology handling with glossary Backend / API Section Saloni expected to explain backend architecture, APIs, and data storage UI & Demo Presentation Santhosh and Aakarsh to demonstrate frontend interface Explanation of usability design for triage nurses Focus on simplicity and emergency-context efficiency Login functionality included but not emphasized Login design rationale: Only authentication provided No user creation feature Backend-controlled user accounts for security Data Pre-processing Explanation Kushagra assigned to explain model pre-processing steps
3 | Demo structure planning | All | Agreed presentation flow: Problem and background System architecture Backend overview Live demo of application Future work UI screenshots not required since live demo will be show
4 | Demo readiness status | All | Integration between frontend and backend still pending Core translation functionality largely implemented Remaining work involves connecting components Non-critical features may be disabled if unstable Team agreed: Demo must be functional before client/tutor session Core translation feature is mandatory
5 | Integration testing plan | All | Aditya to push latest model updates Santhosh to complete frontend-backend integration Quick verification meeting scheduled next morning Troubleshooting to occur if integration fails
6 | Client/product owner meeting preparation | All | Product owner (Kushagra) to present demo to supervisor/client Meeting scheduled for 3:30 pm Purpose: show development progress and gather feedback Demo does not need formal presentation slides Feedback expected mainly on: UI usability Workflow efficiency Click complexity Overall system concept
7 | Scheduling constraints | All | Team members discussed availability due to: Tutorials University commitments External activities Agreed to meet at 9:00 am online for integration review
8 | Outstanding tasks | All | Identified pending work: Final integration of components Completion of presentation slides Testing demo functionality Rachael to provide initial slide draft for review
Open Actions
Item | Action/Discussed | Deadline
1 | Complete frontend-backend integration | Before demo
2 | Push latest model updates | Immediate
3 | Prepare presentation slides | Before tutorial
4 | Review demo functionality | Next meeting
5 | Conduct integration test meeting | 9:00 am next day
6 | Prepare for product owner demo | Same day
Questions for Mentor
None
Questions for Client
Feedback on prototype usability and workflow